## team delta
Team Delta - Mobile Banking Application
Methodology: Scrum ¦ Sprint Length: 2 Weeks ¦ Total Sprints: 7 ¦ Duration: Jun–Oct 2026 ¦ Members: 7
👥 TEAM ROSTER
# | Member Name | Role | Email | Sprint Focus | Pts/Sprint | Availability | Status
1 | Manognya Jain | Scrum Master | 24211a6772@bvrit.ac.in | Management and team checkup | 5 | 100% | Active
2 | Shrestha | product owner | 24211a6777@bvrit.ac.in | Client Updates | 3 | 50% | Inactive
3 | Srawanthi | Frontend Developer | 24211a67c1@bvrit.ac.in | User dashboard | 5 | 100% | Active
4 | Geetha | DevOps Engineer | 24211a67c0@bvrit.ac.in | Jenkins Updation and worklow management | 3 | 100% | Active
5 | Manasa | tester and QA engineer | 24211a6765@bvrit.ac.in | Dashboard testing | 4 | 100% | Active
6 | Ramyasri | Backend Developer | 25215a6707@bvrit.ac.in | User dashboard | 5 | 100% | Active
7 | Abhiram | Designer | 24211a67b2@bvrit.ac.in | user module design | 5 | 100% | Active
📅 SPRINT PLAN — 7 SPRINTS | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Sprint # | Sprint Goal | Start Date | End Date | Duration | Committed Pts | Completed Pts | % Done | Velocity | Defects Found | Defects Fixed | Carry Over | Status | Review Date | Retro Date | Notes
Sprint 1 | Requirement Analysis & Planning | 2026-06-19 | 2026-06-28 | 9 days | 10 | 10 | 100% | 10 | 3 | 3 | 0 | Completed | 2026-06-26
Sprint 2 | Authentication & MPIN and database | 2026-06-29 | 2026-07-12 | 14 days | 10 | 9 | 90% | 9 | 3 | 2 | 0 | Completed | 2026-07-10
Sprint 3 | User Management Module | 2026-07-24 | 2026-08-08 | 14 days | 10 | 8 | 80% | 8 | 3 | 1 | 1 | Incomplete | 2026-08-07
Sprint 4 | Column1: Account Management and CI/CD
Sprint 5 | Column1: Transfer and docker
Sprint 6 | Column1: Notifications and Payments&profile
Sprint 7 | Column1: Monitoring & Final Delivery
TOTALS | Column6: 27; Column7: 90%; Column8: 9; Column9: 9; Column10: 6; Column11: 1
🔄 DAILY STAND-UP LOG (Current Sprint)
Member | Column1: Role; Column2: Yesterday's Work; Column3: Today's Plan; Column4: Blockers; Column5: Story Pts; Column6: Task Status; Column7: Help Needed?
Manognya | Column1: Scrum Master; Column2: Updates collected from team; Column3: Report planning and client meetup; Column4: none; Column5: 5; Column6: Done; Column7: no
Abhiram | Column1: Designer; Column2: Upadting git; Column3: client meetup; Column4: none; Column5: 5; Column6: Done; Column7: no
Srawanthi | Column1: Frontend; Column2: payment modules; Column3: payment modules; Column4: none; Column5: 5; Column6: Done; Column7: no
Shreshta | Column1: Poroduct owner; Column2: -; Column3: -; Column4: none; Column5: 5; Column6: Done; Column7: no
Manasa | Column1: QA; Column2: Testing backend; Column3: Upadting and clearing issue; Column4: none; Column5: 4; Column6: Done; Column7: no
Ramyasri | Column1: Backend; Column2: payment modules; Column3: payment modules; Column4: none; Column5: 5; Column6: Done; Column7: no
Geetha | Column1: DevOps (Docker/K8s); Column2: raised an issue for tester updation; Column3: Jenkins and workflow check; Column4: none; Column5: 4; Column6: Done; Column7: no
📈 SPRINT METRICS & BURN-DOWN SUMMARY
Sprint | Column1: Committed; Column2: Completed; Column3: Remaining; Column4: Velocity; Column5: % Done; Column6: Defects; Column7: Fix Rate
Sprint 1 | Column1: 10; Column2: 10; Column3: 0; Column4: 10; Column5: 100%; Column6: 7; Column7: 7
Sprint 2 | Column1: 10; Column2: 10; Column3: 0; Column4: 10; Column5: 100%; Column6: 2; Column7: 2
Sprint 3 | Column1: 10; Column2: 10; Column3: 0; Column4: 10; Column5: 100%; Column6: 2; Column7: 2
Sprint 4
Sprint 5
Sprint 6
Sprint 7