## Sprint Backlog
Sprint | Week | Sprint Goal | Tasks | Responsible Members | Deliverables
Sprint 1 | Week 1 | Requirement Analysis & Planning | Requirement Gathering, Stakeholder Analysis, User Story Creation, Product Backlog Creation, Sprint Planning | Shrestha (Product Owner), Manognya (Scrum Master) | SRS Document, Product Backlog, Sprint Plan
Sprint 2 | Week 2-3 | System Design & Architecture | Architecture Design, Database Design, API Design, UI Wireframes, Technology Stack Finalization | Srawanthi (Frontend Developer), Ramyasri (Backend Developer) | Architecture Diagram, ER Diagram, API Documentation, UI Wireframes
Sprint 3 | Week 4-5 | User Management Module | Login Page Development, Registration Page Development, Authentication APIs, Database Setup | Srawanthi (Frontend Developer), Ramyasri (Backend Developer) | Authentication Module, User Management Module
Sprint 4 | Week 6-7 | Account Management | User Dashboard, Transaction Module, Admin Module, Transaction History Module | Srawanthi (Frontend Developer), Ramyasri (Backend Developer) | Transaction History, User Dashboard
Sprint 5 | Week 8-9 | Transfer and Docker | Order Management APIs, Payment Gateway Integration, GitHub Repository Setup, Jenkins Pipeline Configuration, Docker Containerization | Ramyasri (Backend Developer), Geetha (DevOps Engineer) | Payment Module, CI/CD Pipeline, Docker Images
Sprint 6 | Week 10-11 | Notifications and Payments Profile | Alerts, Login Audit, Payment History, Admin Module Updation | Srawanthi (Frontend Developer), Ramyasri (Backend Developer) | Admin Dashboard, Payment History and Dates
Sprint 7 | Week 12-13 | Testing, Deployment & Project Release | Functional Testing, API Testing, Regression Testing, Bug Verification, Render Deployment, Monitoring Setup, Final Documentation | Manasa (QA/Test Engineer), Geetha (DevOps Engineer), Entire Team | Test Reports, Render Deployment, Monitoring Dashboard, Final Project Release